## Brahmini_2021
Date | Project/Task | Initial Estimate in Hours | # Hours Spent today | Tasks to be Started | Tasks In Progress | Tasks Completed | Any Issues | Actual Hours to complete the task | Comments | Feedback from Lead
2021-09-03 | Java Web Development Underhood Video | 2 hrs | 2 hrs | I have to practice the examples practically that are learned until now | Practicing the examples | watched and learned up to 35 videos and practiced up to 20 videos | No | 10 hrs | Understanding Jsp and sevlets from the view of practical business projects
| Core Java Training | 1 hr | 30 minutes | Practice about abstract and interface keywords | Practicing enum | Practiced final , super Keywords | NO |  | Need to practice more
| Spring_TestInterface |  | 4 and half hrs | fetch the required user data from the database | observe the tables data that is linked with interface and understand the code | created a new paytm_transaction report interface | Little bit confusing |  | Trying to understand
2021-09-04 | Java Web Development Underhood Video | 5 hrs | 5 hrs | have to practice the remaining examples practically in system and trying to complete the remaining course | Practicing the examples | Course completed up to 45 % and practice sessions completed up to 37 % |  | 10 hrs
| Core Java Training | 2 hrs | 2 hrs | complete the interface topic of core java part 2 module. | Practicing the examples about interface | Practiced the enum and abstract keywords
| Paytm_ transaction report | 50 hrs | 1 hr | Develop an paytm_transaction_report interface to fetch the data from the data base | Observing the code and the tables in the database and their connection | Observed the flow of the code and tables in the database |  |  | yet to be started
2021-09-06 | Java Web Development Underhood Video | 2 hrs | 1 and half hour | Have to practice the remaining examples practically in system | Practicing the examples in the system | Completed the course upto 50 % and practiced up to 40% |  | 10 hrs
| Core Java Training | 1 hr | 0 hr | Practice about interface examples | Practicing interface examples | None
| Paytm_ transaction report | 5 hrs | 6 and half hours | Fetch the required data from the wiPay scale table | Understanding the flow and fetching the data from the request_temp table | created paytm_transaction report interface and fetched the required data from the table request_temp using user id, order id, trans id. |  | 24 hrs
2021-09-07 | Java Web Development Underhood Video | 1 hr | 0 hr | Have to practice the remaining examples practically in system | Practicing the examples in the system | Completed the course upto 50 % and practiced up to 40% |  | 10 hrs
| Core Java Training | 2 hrs | 2 hrs | Study about exception handling | attended the class about interfaces | Studied about interfaces
| Paytm_ transaction report | 6 hrs | 6 hrs | Fetch the required data from the wiPay scale table | fetch the required data from the data base | fetched the required user data from the request_temp and wipay_action table based on trans_id order_id ,msisdn |  | 18 hrs
2021-09-08 | Java Web Development Underhood Video | 1 hr | 1 hr | Practice the remaining examples | Practicing the examples in the system | Practiced the examples up to 45 % |  | 10 hrs
| Core Java Training | 2 hrs | 2 hrs | learn about exception handling | Practicing examples about the interfaces in system | Studied about exception handling
| Paytm_ transaction report | 6 hrs | 5 hrs | add the remaining data in the interface | fetch the required data from the data base | fetched the required user data from the remaing tables paytm_history & request based on trans_id order_id ,msisdn |  | 13 hrs
2021-09-09 | Java Web Development Underhood Video | 3 hrs | 4 hrs | Practice the remaining examples and watch&learn the reamaining videos | Practicing the examples in the system | Practiced the examples up to 50 % and completed the course upto 60% |  | 10 hrs
| Core Java Training | 3 hrs | 3 hrs | learn about exception handling | Practicing examples about the exception handling in system and learning about files and streams | Studied about some remainig topics in exception handling and practiced the examples in my system
| Paytm_ transaction report | 3 hrs | 1 hrs | add the remaining data in the interface | fetch the required data from the data base | fetched the required user data from the remaing tables paytm_history & request based on trans_id order_id ,msisdn. Along with that added some functionality in interface |  | 10 hrs | fetched the user data from almost all tables
2021-09-11 | Java Web Development Underhood Video | 5 hrs | 5 hrs | Practice the remaining examples and watch&learn the reamaining videos | Practicing the examples in the system | Practiced the examples up to 60 % and completed the course upto 66% |  | 10 hrs
| Core Java Training | 3 hrs | 3 hrs | learn about files and streams | Practicing examples about the exception handling in system and learning about files and streams | Studied about some remainig topics in exception handling and practiced the examples in my system and interfaces
| Paytm_ transaction report | 0 hrs | 0 hrs | add the remaining data in the interface | fetch the required data from the data base |  |  | 10 hrs
2021-09-14 | Java Web Development Underhood Video | 3 hrs | 5 hrs | Practice the remaining examples on jstl, ajax and watch&learn the reamaining videos | Practicing the examples on mvc concepts in the system | Practiced the examples up to 65 % and completed the course upto 75% |  | 10 hrs
| Core Java Training | 3 hrs | 3 hrs | learn about streams | Practicing examples about the exception handling in system and learning about files and streams | Attended the core java class on exception handling. Studied about some remainig topics in exception handling and practiced the examples in my system
| Paytm_ transaction report | 2 hrs | 0 hrs | add the remaining data in the interface | fetch the required data from the data base |  |  | 10 hrs
2021-09-15 | Java Web Development Underhood Video | 3 hrs | 3 hrs | Practice the remaining examples on ajax and watch&learn the reamaining videos | Practicing the examples on in the system | Practiced the examples up to 80 % and completed the course upto 90% |  | 10 hrs
| Core Java Training | 2 hrs | 2 hrs | learn about streams | Practicing examples about the streams in system and learning about files and streams | Studied about servlet api and jdbc api interface implementation and practiced the examples in my system
| Paytm_ transaction report | 0 hrs | 0 hrs | add the remaining data in the interface | fetch the required data from the data base |  |  | 10 hrs
| wipay | 2 hrs | 2 hours | learn about the billing flow in wipay | setup the wipay project in eclipse with out any errors | Learned about svn of comparing the codes and how to commit using svn
2021-09-16 | wipay | 5 hrs | 6 hours | Understand the wipay billing flow at code level | Started the code level understanding at Bill.java (parameter validation) | Learned about actual billing flow (business flow) from user to operator . And also got a clear idea about when wipay(3rd party )comes into the picture in this process. And also experienced it practically.
| Java Web Development Underhood Video | 2 hrs | 2 hrs | Practice the remaining examples on ajax, json, asynchronous servlets. | Practicing the example of connecting to the data base in the system | Practiced the examples up to 80 % and completed the course | got an exception in the orderRecieved servlet while fetching the data from the data base | 10 hrs
17/09/2021 | wipay | 7 | 8 | Learn about bill.java (url hitting) | Understanding the bill flow at code level and learning the validations in APIValidation.java | Prepared a document about the bill flow (What I havae understood) and learned about sms billing flow.
18/09/2021 | wipay | 5 | 1 | Learn about bill.java (url hitting) | Understanding the bill flow at code level and learning the validations in APIValidation.java
| Merchant mail template interface | 4 hrs | 5 hrs | add the template details in to database and edit them | trying to add the template details into data base | Created add/edit interface for merchant mail template .
| core java | 1 hr | 2 hrs | learn about streams | Learning about files | Attended the core java class and learned about files concepts such as how to create empty files and directories using java files .
20/09/2021 | wipay | 3 | 2 | Learn about bill.java (url hitting) | Understanding the bill flow at code level and learning the validations in APIValidation.java | Understood the code flow of sending mail to users about the billing and leaned about deploying the live project in different servers and experienced practically
| Merchant mail template interface | 4 hrs | 5 hrs |  |  | created merchant mail interface and added &edited the data as well as fetched the data from the data base |  |  | completed
| core java | 1 hr | 1 hr | learn about streams | Learning about streams | Attended the core java class and learned about streams concepts Inputstream and its subclass classes
21/09/2021
| core java | 1 hr | 1:30 hr | learn about streams and practice the examples | Learning about streams | Attended the core java class and learned about streams concepts outputstream and its subclass classes, Buffered Stream, PrintStream
| wipay | 7hrs | 6 and half hours | mail setting changes in wipay | Learning about mail utility.java class flow | Learned about the deployment process and mail sending flow from wipay to user . Practically watched the flow in wipay. Practiced the example for sending mails using javax.mail*
22/09/2021
| core java | 1 hr | 1 hr | learn about streams and practice the examples | Learning about streams | Attended the core java class and learned about streams concepts prints¦tream class and examples
| wipay | 7hrs | 7 hours | mail setting changes in wipay | Have to make the changes in the mailutility.java file | Added an extra sendMail method in MailUtility to fetch the details from wipay_smtp_settings table. Along with that done a javax mail sample program to send mail using java api
23/09/2021
| wipay | 7hrs | 8 hrs | try to avoid ssl certificate to send mails using java | trying to avoid ssl certificate in javax mail | Added an extra sendMailAWS method in MailUtility to fetch the details from wipay_smtp_settings table. Along with that tested aws sample mail locally. And tested using unitTesting.java in dev.wicore.in (stage). But not deployed in live.
24/09/2021
| core java |  | 1 and half hour | learn about streams | Practicing streams | Attended the core java class and learned about streams concepts datastreams
| wipay | 7hrs | 6 and half hrs | cbm setup | cbm setup | Tested the bemobi mail on live
25/09/2021
| core java |  | 2 hours | serialization and deserialization | Practicing streams | Attended the core java class and learned about streams concepts datainputstream and dataoutput stream
| wipay | 7hrs | 6 hrs | learn about cbm code flow and wipay | learning the cbm flow | Done setup in eclipse and learned about the connection and data fetching from tables
27/09/2021
| wipay | 3 hrs | 1 hr | Learn about url hitting | Observing the flow | practiced about unsubscription url hitting. And sent unsubscription message to user
| WiPayOperatorSMSCallbackQueueMO | 5 hrs | 7 hrs | learn about cbm code flow and wipay | learning the cbm flow | Learning about the cbm flow. Along with that prepared a web sequence flow of sms billing ( idea and vodafone)
28/09/2021
| core java | 1 hr | 1 hr | transient data | Practice serialization and deserialization examples | Attended the core java class and learned about serialization and deserialization concepts
| WiPayOperatorSMSCallbackQueueMO | 5 hrs | 7 hrs | learn about cbm code flow and wipay | learning the cbm flow | Learning about the cbm flow. Watched the logs of smsbilling and learned about the merchant validation & callbacks, short code request to operator, billing price validations by comparing the logs and code.
29/09/2021 | core java | 1 hr | 2 hrs | Networking | practice socket networking and transient data examples | Attended the core java class and learned about transient data, bridge streams, PipedStreams and networking concepts
| WiPayOperatorSMSCallbackQueueMO | 5 hrs | 5 hrs | learn about cbm code flow and wipay | learning the cbm flow [code level] | Learned clearly about the idea, vodafone sms billing flow [business flow].
| WiPay Proxy | 1 hr | 1hr | wipay proxy | learning about javascript | learned about how to create javascript objects and its elements
30/09/2021 | core java | 1 hr | 1 & half hrs | Networking | practice socket networking and transient data examples | Attended the core java class and learned about networking concepts
| wipay | 5 hrs | 5 & half hrs | develop a method to store payment gateway histories | develop a method to store payment gateway histories | watched the code flow. Along with that created a pmtgtwy_history table with required parameters, and added a method storeEvent() in postBilling
| wipay cms meeting [liferay] | 1 hr | 1hr |  |  | Attended the liferay conference and understood about their products
2021-01-10 | core java | 1 hr | 1 & half hrs | Networking | practice socket networking and transient data examples | Attended the core java class and learned about networking concepts such as how to send messages from server to client .
| wipay | 5 hrs | 5 & half hrs | Call that method to store values dynamically from server to the table | Call that method to store values dynamically from server to the table | developed a method to store the payment details in pmtgtwy_history table. Also stored the details into the table manually by using UnitTesting.java class.
| retrieving the data from the logs | 1 hr | 1hr |  |  | retrieved the logs of billing data of previous month
2021-02-10 | core java | 1 hr | 3 & half hrs | Networking |  | Practiced the networking concepts such as socket classes and http request types
| wipay | 5 hrs | 2 & half hrs | Call that method to store values dynamically from server to the table | Call that method to store values dynamically from server to the table | Observing the flow of the postbilling process by following the SubCB.java and SubRD.java classes
| fetching the data from the logs | 1 hr | 1hr |  |  | fetched the today logs of billing data using cat command
2021-04-10 | core java | 1 hr | 3 hrs | servlets | Practice about networking concepts and servlets | Attended the class about networking and servlets introduction…
| wipay | 5 hrs | 4 | Call that method to store values dynamically from server to the table | Have to test the data is storing in the pmtgtwy_history table and find the error of not getting count value for vo in WiPay Action Summary Report Hourly | called the storeEvent method in SubCB.java and SubPostBillProcess.java dynamically..
2021-05-10 | core java | 1 hr | 2 hrs | sevlets | Practice about servlets | Practiced about servlet introduction and learned about network programming
| wipay | 6 hrs | 6 hours | call the historystore events method in postbilling dynamically | call the historystore events method in postbilling dynamically | Written an enum class by storing the status messages . Called the storeevents method in prebilling dynamically in various classes and stored the values in database by hitting the billing request url
2021-06-10 | WiPayTest |  | 1 hr |  |  | Learned about how to create & get links and use that links to test the wipay billing process
| wipay | 6 hrs | 7 hours | call the historystore events method in postbilling dynamically | call the historystore events method in postbilling dynamically | Called the storeEvent method in various classes like BillW.jsp, Bill.java, usrauth.jsp etc., and stored the various params including status of the billing process in database [only prebilling].
2021-07-10 | core java | 1 hr | 1 hr | servlets |  | practiced about networking
| wipay | 5 hrs | 2 & half hrs | call the historystore events method in postbilling dynamically | Have to test the data is storing in the pmtgtwy_history table for both the pre billing and post billing processes | called the storeEvent method in SubCB.java and SubPostBillProcess.java dynamically..But not tested
| merchant registration interface |  | 4 and half hrs | store the user data specifically into two tables based on ids | store the user data specifically into two tables based on ids | created a merchant description interface and done the operations such as add edit and stored in the data base. But we have to store the data specifically into two tables at the same time based on foreign key and primary key ids.
2021-08-10 | merchant registration interface | 6 hrs | 8 hrs |  |  | Stored the data specifically into two tables based on single id using the concept of primary key and foreign key. Along with that using the concepts onblur function and ajax call in javascript avoided allowing the duplicate merchant name. And finally stored the data by unique id and unique name.
2021-09-10 | core java | 2 hrs | 2 hrs |  | servlets | Attended the class about servlets, tomcat setup, deploying servlets and servlet life cycle and methods
| merchant registration interface | 2 hrs | 1 hr | billing provider_mapping interface |  | Completed the interface completely by avoiding duplicate entries.
| wipay | 4 hrs | 4 hrs |  |  | called the prebilling store event methods in bill.java and other classes
2021-11-10 | core java | 2 hrs | 1 hr |  |  | practiced about servlet request types, servlet classes
| wipay | 6 hrs | 7 hrs |  |  | Learned about wipay flow and learned about how to retrieve the logs from different servers to get the specified data.
2021-12-10 | core java | 2 hrs | 3 hrs |  |  | studied about multi threading and practiced some examples
| wipay | 1 hr | 1 hr |  |  | examined about pre billing and post billing
| logs | 4 hrs | 4 hrs |  |  | studied about grep & awk commands. Tried to retrieve the required logs from server.
13/10/2021 | core java | 3 hrs | 2 hrs |  |  | practiced multi threading examples
| cbm.jar | 3 hs | 4 hrs |  |  | examined the flow from the business level view
| logs | 2 hrs | 2 hrs |  |  | practiced about how to retrieve the logs from server
14/10/2021 | core java | 2 hrs | 1 hr |  |  | practiced multi threading examples and also done some java hacker rank solutions
| cbm.jar | 3 hs | 3 hrs |  |  | examined the flow from the business level view. And by observing the logs followed the step by step process in coding and along with that understood the business flow using logs
| wipay | 2 hrs | 2 hrs |  |  | fired the pre billing url to know the process of the business flow. And observed the logs
18/10/2021 | cbm.jar | 2 hrs | 1 hr | add the idea sms funcitonality in cbm.jar | Call thestoreSMSHistory() method in the ongoing process flow | Added HistoryEventsDAO.java and HistoryEvents.java classes in cbm.jar
| wipay admin/Wipay Event Summary hourly Report | 2 hrs | 2 hrs |  | Have to retrieve the data from the database. | created aWipay Event Summary hourly Report in WipayAdmin. It is used to retrieve the data from pmtgtwy_history table based on network and merchant. It counts the various request events like BILLREQUEST,VALIDATEORDER etc., per day and per network and merchant
| Logs | 3 hrs | 5 hrs |  |  | Retrieved the logs of vodafone 55321 SMSMO data from 11thoct to 18thoct. After that prepared a document about the logs and log commands. Observed the flow of trouble shooting in payments.
19/10/2021 | cbm.jar | 6 hrs | 4 hrs | add the idea sms funcitonality in cbm.jar | AddingstoreSMSHistory() method in the IdeaIBMBillingProcessor.java class | Added thestoreSMSHistory() method in ideaoffnetThread.java class.
| Logs | 2 hrs | 4 hrs |  |  | Retrieved the logs of September and October Idea SMSMO data of counts and nodes from both the servers. Modified the documentation by adding other logs.
20/10/2021 | cbm.jar | 6 hrs | 4 hrs | have to test the functionality | have to test the functionality | Completed the adding ofstoreSMSHistory() method in ideaoffnetThread.java, IdeaIBMBillingProcessor.java, SMSBillValidation.java classes in cbm.jar
| Wipay Event Summary hourly Report | 2 hrs | 3 and half hrs |  | Have to make the some other changes in the code in order to get the data in a correct manner | Almost completed the interface.Retrieved the data from thepmtgtwy_history table. But the data is not in the correct order
20/10/2021 | cbm.jar | 6 hrs | 6 hrs | have to test the functionality | have to test the functionality | modified the changes adding ofstoreSMSHistory() method in ideaoffnetThread.java, IdeaIBMBillingProcessor.java, SMSBillValidation.java, SMSBILLUTILITY.java classes in cbm.jar and prepared a document
| Wipay Event Summary hourly Report | 2 hrs | 2 hours |  | make the changes if necessary | Completed the interface which retrieves the count of each event by hour and merchant wise.
22/10/2021 | cbm.jar | 8 hrs | 8 hrs |  | have to test the remaining functionality and make other changes | Half of the verification of storing events using storeSMSHistory() method in table is completed. Solved exceptions while running cbm.jar. Along with that prepare a websequence diagram of cbm.jar flow.
23/10/2021 | servlets | 5 hrs | 5 hrs |  |  | attended the class about servlets, servlet methods, mime types, how to call servlet to servlet and what type of data servlet displays in browser and studied about these concepts.
| cbm.jar | 2 hrs | 2 hrs |  | have to test the remaining functionality. | examined about storing of events in sms_history table and done some other changes to store the full data including operator id and order_id in validate_order_request event.
25/10/2021 | servlets and jsp | 1 hrs | 1 hrs |  |  | studied about servlets and jsp
| cbm.jar | 8 hrs | 7 hrs |  | verify and deploy in live | added additional changes in the classes and added commentry wherever the method is called. Along with that observed prebill and post bill process in wipay
26/10/2021 | WiPayTest/ Implement wifi billing testing in WiPayTest | 8 hrs | 8 hrs |  |  | Here we have to implement wifi billing test functionality in order to test the test url's live in dev. So, First of all I have added wifi billing functionality in billing type in wipay test. After made the changes in view test.jsp, link execution.jsp etc., and finally generated the url's.
27/10/2021 | WiPayTest/ Implement wifi billing testing in WiPayTest | 2 hrs | 4 hrs |  |  | Done some changes in Add/Edit Test links using jquery and javascript. Added extra textbox bill_api in Add/Edit and based on bill_api the urls are generated. |  |  | completed
| WiPayProxy/substatus.java | 4 hrs | 4 hrs |  |  | created a substatus.java class and generated the url and passed that string to reqJSON
28/10/2021 | WiPayProxy/substatus.java | 6 hrs | 6 hrs |  |  | done some changes in substatus.java such as assigning the values for mid, cid, msisdn, sign using json object and generated the sign passed to a fireUrl() method in urlutility(newly created) in order to get the response in json format.
| Logs/Bemobi User wise response from Paytm | 2 hrs | 2 hrs |  |  | retrieved the paytm response message from server logs and prepared an excel sheet.
| cbm.jar |  | 1 hr |  |  | tested some events by hitting the url for both vodafone and idea.
29/10/2021 | cbm.jar | 6 hrs | 6 hrs | Test with url |  | Added extra events such as MERCHANTCB, SMSREQUEST,SMSRESPONSE in callbackutility.java and tested again by hitting url
| logs |  | 2 hrs |  |  | Retrieved the logs of idea mo from oct 21 to oct 29.
30/10/2021 | cbm.jar | 6 hrs | 6 hrs | deployment |  | Done some changes and tested with url and the events are storing in sms_history table. Along with that added extra Merchantcb in voda54767.java class.
| core java |  | 2 hrs |  |  | Attended the class about servlets request parameters and html input forms
2021-01-11 | cbm.jar |  | 3 and half hours | deployment |  | done some changes in vodasms billing and tested with urls
| logs |  | half an hour |  |  | Retrieved the logs of idea mo of october 30 and 31.
2021-02-11 | cbm.jar |  | 7 hrs | deployment |  | done some changes in ideasms billing like adding extra columns like status msg, node & stored the required data based on events and tested with urls
| WiPayTest/sms Billing |  |  |  | add the sms billing and test the links. | Done the required analysis
2021-03-11 | WiPayTest/sms Billing | 6 hrs | 7 hrs |  | dynamic validation is required. | done the required changes to get the links. But dynamic validation is required and to process for the billing test. Have created two separate links for idea and vodafone
2021-05-11 | WiPayTest/sms Billing | 8 hrs | 5 hrs | Completed |  | Added sms billing functionality in wipayTest. Created vodafone and idea links. And tested it practically.
| cbm.jar&WiPay/idea and vodafone bill (StoreSMSHistory) |  | 1 hr | Completed |  | Done some changes in cbm.jar to store the operator bill request and response events in history table and tested idea and vodafone billing by using WiPayTest (SMSBilling functionality).
| Servlets |  | 2 hrs |  |  | Attended the class and learned about maven build tool and how to add dependencies, jars. Along with that learned about how to build the war file in maven and tomcat server.
2021-06-11 | WiPayTest/sms Billing |  | 2 hrs |  |  | Added some changes in viewtest.
| Servlets |  | 3 hrs |  |  | practiced about how to create maven project and build the project
| wipay docs/ paytm api1.7 |  | 2 hrs |  |  | studied about the paytm api 1.7
2021-08-11 | WiPayTest/sms Billing |  | 2 hr | Completed | completed | Added some changes in wipaytest.jsp where default radio buttons and prepared a document based on the changes that I have made in wipayTest project for adding sms and wifi billing functionality
| wipay docs/ paytm api1.7 |  | 3 hrs |  |  | studied the paytm api 1.7 document and observed the flow of Bill.java class in paytm.
| cbm.jar / logs / wipayTest |  | 3 hrs |  |  | Explained the flow of cbm.jar, how to grep the logs and changes made in wipay test to other colleagues.
2021-09-11 | wipay docs/ paytm api1.7 |  | 3 hrs |  |  | studied the paytm api 1.7 document and observed the flow of Bill.java class in paytm.
| WiPayTest/Login check |  | 4 hrs |  | We have to store the credentials dynamically. And also have to create cookies. | created a login interface in WiPayTest with login.jsp page and created a user_master table in WiPayTest database and entered the user credentials manually and tested the login page with the manual user credentials and redirected to WiPayTest[index.jsp] page.
2021-10-11 | WiPayTest/Login check |  | 1 hr |  | We have to store the credentials dynamically. And also have to create cookies. | Tried to add the captcha and login successfully with manual data.
| WiPay/SamsungHQ sub |  | 6 and half hours |  |  | Examined the code flow started from Bill.java. Along with that studied the api doc 2.0 and changed the parameters by observing logs, docs, urls.
2021-11-11 | WiPayTest/Login check |  | 2 hr |  | We have to store the credentials dynamically. And also have to create cookies. | dumped the required tables from wipaydb database to wipayTest db and edited the login page
| WiPay/SamsungHQ sub |  | 6 hours |  |  | Observed the code flow and logs. updated the existed project api documentation 1.7
2021-12-11 | Wipay/Paytm |  | 5 hours |  |  | examined the logs and code of paytm and got the request, validate order, redirection, callback parameters and made a document. After that observed the logs in live server
| cbm.jar |  | 3 hours |  |  | Explained the flow of cbm.jar, how to hit the url and identify the logs. Also how to check in wipaytest and see the results stored in database.
13/11/2021 | WiPay/SamsungHQ sub |  | 4 hours |  |  | Observed the code flow and logs.
| Servlets |  | 3 and half hrs |  |  | studied and practiced about generic servlets and html to html navigation examples. Attended the class and learn about the topi c “more about request object topic”
15/11/2021 | Servlets |  | 3 hrs |  |  | Practiced the servlets examples using maven
| WiPay/SamsungHQ sub |  | 5 hours |  |  | Examined the flow of samsungHq event which starts from paytm Bill.java and followed the code and required parameters for SamsungHq and observed the logs for event subscription in SamsungHq
16/11/2021 | WiPay/SamsungHQ |  | 8 hours |  |  | Observed the flow and prepared a document aboutMapping the payload parameters to the actual DB tables. After that examined the changes to be made in api1.8 updated version.
17/11/2021 | WiPay/SamsungHQ |  | 8 hours |  | Need to prepare a clear document about tables mapping | Observing the code flow clearly by comparing it with api document & current dev logs and tested using urls found in dev wipaydb database, but got nothing. Edited the document about Mapping the payload parameters to the actual DB tables. | Not clear about the doucumentation
18/11/2021 | WiPay/SamsungHQ |  | 8 hours |  | Need to prepare a clear document about tables mapping | Got a clear clarity about preparing the documentation. Started writing the documentation from the start and completed half of the document [Writing the overall codeflow what I have understood upto now].
19/11/2021 | WiPay/SamsungHQ |  | 8 hours |  | Observe at VI Merge functionality in cbm.jar | Prepared a document of Mapping the payload parameters to actual Database tables along with the code flow. Observing the code flow of cbm.jar
20/11/2021 | cbm.jar |  | 6 hours |  |  | examined the code flow by comparing with logs.
| WiPay/SamsungHQ |  | 2 hours |  |  | Observed Samsung hq document billing flow.
22/11/2021 | core java |  | 3 hours |  |  | Attended the class and learned about HTML page with two or more input forms and practiced the 5 servlet projects in maven build tool.
| cbm.jar |  | 5 hours |  |  | Preparing cbm.jar code flow document by observing the code and logs.
23/11/2021 | cbm.jar |  | 8 hours |  |  | Understanding the flow and preparing a document based on the code flow.
| core java |  | 1 hours |  |  | Attended the class and learned about RequestDispatching an types of requestdispatching .
24/11/2021 | cbm.jar |  | 8 hours |  |  | Understanding the flow and preparing a document based on the code flow. And observing the code where to make the changes in the project according to cbm.jar
25/11/2021 | cbm.jar |  | 8 hours |  |  | Observing the database queries in methods, where we are selecting them and inserting. And following the code line by line along with logs.
26/11/2021 | cbm.jar |  | 8 hours |  |  | Created a replica of ideaOffnetThread named as VIOffnetThread and writing the code by following the code and observing & preparing a document of list of tables that are needed to insert an extra row for vi
27/11/2021 | cbm.jar |  | 6 hours |  |  | Continuing the writing of viOffnetThread by following the logs and noting down the changes required in the queries.
29/11/2021 | cbm.jar/ changes for vi |  | 8 hours |  |  | Identified the tables that contains operator id and prepared a document based on the insertions. Attended the call
30/11/2021 | cbm.jar/ changes for vi |  | 8 hours |  |  | Identified the tables that need proper insertions in the required tables for vi. And made a document of insertions of queries and changes. And created sql insertion document for each table in .sql format.
2021-01-12 | cbm.jar/ changes for vi |  | 8 hours |  |  | Modified the changes in the queries and inserted the data required for Vi in local database. Along with that created a replica of idea_54767_front.java and named as Vi_54767_front.java which is a servlet class and hitted the url and tested the class. Its working fine.
2021-02-12 | cbm.jar/ changes for vi |  | 8 hours |  |  | Trying to test in local. Created getMTAccessToken() method in callbackUtility.java class in sendMTMessage method.
2021-03-12 | cbm.jar/ changes for vi |  | 7 and half hours |  | Create a xmlRequest in soap format | created getMobileTerminationAccessToken() in both sendMTMessage and processMTMessage methods. Created token_config table in localdb and inserted the required data manually.
| System hanged |  | 30 minutes | have to increase RAM |  |  | storage space is almost filled in c drive
2021-04-12 | cbm.jar/ changes for vi |  | 8 hours |  |  | done the changes in the processMTMessage and sendMTMessage by making changes in the query. Created soap xml format standalone class by giving manual data and tested it to generate the SMS MT Request.
2021-06-12 | servlet class |  | 1 hr | Learn about Connection pooling. | Practice the examples | Attended the class about initialization parameters , servlet context, servlet config, servlet annotations and learned about them.
| cbm.jar / changes for vi |  | 7 hrs | Testing in stage | creating the replica of the existing classes of idea for Vi | Added the extra method namely processXMLMTfor vi in sendMTMessage and created some classes replications for Vi.
2021-07-13 | cbm.jar / changes for vi |  | 8 hrs | Testing in stage |  | created the replication of SMSBillUtility.java as ViSMSBillUtility.java, ViSMSBillingProcessor, SMSBillValidation, SMSCallBacKUtility classes in Vicbm.jar project. And deployed in dev and observed the logs.
2021-08-12 | cbm.jar / changes for vi |  | 4 hrs | Testing in stage | Working the Changes to be made in the code | Reviewed the code and noted some changes to be made in the code.
| deployment |  | 4 hrs | Need to deploy cbm.jar changes in the live |  | Deployed the changes in the wipay on live
2021-09-12 | deployment |  | 5 hrs |  |  | Deployed the changes in the CBM.Jar on live and learned about the deployment procedure. Along with that observed the billing and exceptions.
| cbm.jar / changes for vi |  | 3 hrs | Testing in stage | Working the Changes to be made in the code | Done the changes required in the viOffnetThread.java and other clases.
2021-10-12 | cbm.jar |  | 4 hrs |  |  | Done some changes in the sms_history and learned about deployment procedure and logs checking. Along with that reviewed the code once again.
| cbm.jar / changes for vi |  | 4 hrs |  |  | reviewed the code and done some changes wherever it is required.
20/12/2021 | cbm.jar / changes for vi |  | 8 hrs |  | Got ssl handshake exception. Trying to solve it. | Deployed in the staging. Got multiple exceptions due to inserting new data for vi in various tables. Solved the exceptions line by line by deploying and hitting the urls multiple times.
21/12/2021 | WiPay/ vodafone changes |  | 3 hrs |  | Need to deploy in live | Done some changes like storing circleId, circle name in smsHistory inorder to store vodafone records
| cbm.jar/ Vi changes |  | 5 hrs |  | Need to deploy in live | Merged the code for both Idea and Vi in a single project. Done some additional changes in Vi to store all the records in smshistory.
22/12/2021 | WiPay/ vodafone changes |  | 8 hrs |  |  | Deployed in staging and checked the exceptions and sorted them. After that deployed in live. And its storing the records in sms_history fine.
| cbm.jar/ Vi changes |  |  |  | Execute the scripts in the database for Vi. Need to check the billing for vi by hitting the url using test credentials in live. | Deployed in staging and checked the exceptions and cleared all the exceptions by making somoe changes in the code. After that deployed in live [both idea and vodafone]. Its working fine [Only idea] and storing the records in sms_history table.
23/12/2021 | cbm.jar/ Vi changes |  | 5 hrs |  | clear the exceptions and test in live to make bill success | Deployed in live and started testing. Along with that executed the required scripts in live database for Vi. While testing, billing is stopped due to required changes in the code and database. Working to make the bill success by clearing the exceptions by making changes step by step.
| dumping the table in separate database |  | 2 hrs |  |  | Learned about the basics of dumping a table to another database.
| checking samsungHQ logs |  | 1 hrs |  |  | retrieved the logs of required data
24/12/2021 | cbm.jar/ Vi changes |  | 6 hrs |  | clear the exceptions and test in live to make bill success | Done some changes and executed remaining scripts and tested up to storing Balance request. Getting Balance check Response failure , so working on it.
| cms seminar |  | 2 hrs |  |  | Learned about cms.
25/12/2021 | cbm.jar/ Vi changes |  | 8 hrs |  | clear the exceptions and test in live to make bill success | Tested the billing of Vi Operator. Some changes need to be required. Checked the dumping of callback_queue_lowbal_processed table. And checked the storage in 19 server. And logs are working fine
27/12/2021 | cbm.jar/ Vi changes |  | 6 hrs |  | Make bill success in live with new MT credentials | New MT credentials are added in live db. And documented the required changes in Vi for both check balance and MT requests. Along with that fetched the sample records from sms_history for both Idea and Vodafone and made it into a excel sheet to reduce the no. of records in the table based on our requirement.
| Errors and exceptions in both 13 and 152 server |  | 1 hr |  | Handle the exceptions | Checked whether there are newly added exceptions are not in both the 13 and 152 server. Old exceptions are documented.
| wiapp |  | 1 hr |  |  | Checked the Wiapp website is working properly or not. Documented the functionalities that are not working properly
28/12/2021 | cbm.jar/ changes for vi / Idea_Vodafone changes |  | 7 hrs |  | Once again deployment need to be done to update the changes made in cbm.jar | Documented the list of credentials needed to be changed for balance check and MT request. Made the changes in the Idea/Vodafone/Vi by deleting the BALANCE_CHECK_RESP and BALANCE_CHECK_REQ records in sms_history. Only one record BALANCE_CHECK_RESP success is made to be stored. Along with that dynamically added the username and password for soap request from sms_billing_auth_info credential from group_cbs. All these are tested successfully in dev server.
| Logs |  | 1 hr |  | Handle the exceptions | Observed the logs in both 152 & 13 servers and checked if there are any abnormalities are present
29/12/2021 | Logs |  | 3 hrs |  | Need to handle the exceptions | Observed the logs in both 152 & 13 servers and checked if there are any abnormalities are present. Along with that documented the errors and exceptions occurred in both 13 & 152 servers into a word document. And we need to handle the exceptions
| cbm.jar/ Vi changes |  | 4 hrs |  | Need to deploy in live | committed the changes done in cbm.jar and WiPay project for Balance check and MT Messages into svn.
| deployment |  | 1 hr |  |  | done the deployement of WiPayAdmin.war and observed the logs and billing.
30/12/2021 | cbm.jar/ Vi changes |  | 8 hrs |  |  | Done the changes in the processMTMessage and sendMTMessage by making changes in the getAccesstoken() method. And also added accesstoken in these methods. Handled the exception and server error. Deployed both WiPay and Cbm.jar successfully in both 152 and 13 server. Tested Vi in the servers and billing happened successfully.
31/12/2021 | logs |  | 1 hr |  |  | Observed the logs in both 152 & 13 servers and checked if there are any abnormalities are present after deployment. Along with that observed the truncation of the table wipay_tp_config in wipaydb .
| WiPayDBMS |  | 7 hrs |  |  | Examined the overall code for WiPayDBMS which is used to backup the database tables. Prepared a document about the code flow in WiPayDBMS.

## Brahmini_2022
Date | Project/Task | Redmine_Ticket Number | Initial Estimate in Hours | # Hours Spent today | Tasks to be Started | Tasks In Progress | Tasks Completed | Any Issues | Actual Hours to complete the task | Comments/Notes | Feedback from Lead | Final Product Delivered
2022-03-01 | WiPayDBMS |  |  | 7 hrs |  | Need to deploy in live | Observed the code thoroughly and found out the purpose of the columns wbt_source_table_last_ts, wbt_timestamp, wbt_backup_before_days, wbt_day_of_the_month which plays a major role[time stamps]. And based on the requirement, changed the code by adding additional connection for wicms where we want to take backup for the tables. And deployed on dev server and checked the flow once.
| logs |  |  | 1 hr |  |  | Checked the logs. Observed the database by continuously observing the sms_history count and executed the query to find the day wise data in live. Along with that retrieved the number of requests got in WiCoReServer, WiCoReServer77, WiCoReServer88 using grep and awk command
2022-04-01 | WiPayAdmin |  |  | ½ hour |  |  | Deployed WiPayAdmin in live server. And checked whether there are any exceptions or not.
| sms_history/Database |  |  | 2 hrs |  | Need to modify the document: 1. Order of the events. 2. storing of urls | Retrieved the sms_histroy insert events from data base and made it into a document records
| WiPayDBMS |  |  | 2 hrs |  |  | Deployed the WiPayDBMS project in live server and ran it. Observed the following observations: 1. Whether backup is happening or not. Back up of request table is done. It is moved to request_history table. And the data in the request table is deleted. 2. Backup of other tables is done into csv file.
| Idea_SMSMO_aggregation / record insertion |  |  | 3 and half hours |  | Need to store the remaining data and update in the sms_history_aggregation_reports | Need to store the data from dec 1st to dec 26th in sms_history_aggregation_reports manually. For that done the following things: 1. First of all retrieved the data from the logs daywise [done upto 17th dec]. 2. After that stored the data in the excel sheet.
2022-05-01 | Data Extraction/ Vodafone& Idea |  |  | 7 and ½ hours |  | Need to validate the table and export these data in sms_history_aggregation_hourly table in live database | 1. Extracted the idea and vodafone smsmo data by circle and node wise from logs [both 13 & 152 servers] for 26 days. 2. Inserted these day wise data in a excel sheet. 3. And exported all these data to database by creating a sample table in dev server to check whether it is working or not. Inserted the data into the sample table successfully.
| wiapp/ Wicontent |  |  | ½ hour |  |  | Learned about the wiapp and wicontent projects.
2022-06-01 | Data Extraction/ Vodafone& Idea |  |  | 1 hr |  |  | 1. Validated the table data by comparing them with the logs. 2. After that exported the data in sms_history_aggregation_hourly table in live database. 3. After that again validated the data by comparing with the WiPay Action Summary Report. And updated to Abhishek
| sms_history reports |  |  | 2 hrs |  |  | 1. Modified the data in the excel sheet by adjusting the actions in proper order based on billing process. 2. Also listed the reason for “why the urls are not storing in the actions”
| WiPayAdmin |  |  | ½ hr |  |  | Deployed in the live by making some changes.
| WiPayDBMS |  |  | 2 ½ hrs |  |  | Made a document by explaining all the columns in the wipay_backup_tables with examples.
| WiPayDBMS |  |  | 2 hrs |  | Need to create an interface and display the status of the backup done in each table. | 1.The reason of creating an interface based on backup tables is to know the daily status of the backup tables. 2. So, created a menu in WiPayAdmin in dev.
2022-07-01 | WiPay Backup Tables interface | 1617 | 24 hours | 6 hrs |  | Need to improve the look and feel of the interface may be in a graphical way | Completed the interface by showing the regular running status. Adding also completed
| wipaydb tables doc |  |  | 2 hrs |  |  | added some table informations in the wipaydb doc
2022-10-01 | WiPay Backup Tables interface | 1617 | 24 hours | 7 and ½ hours |  | Backup has to be done when we enter the required backup details in this page and click on submit, then backup of the table has to be done simultaneously | 1. Added external features in the interface such as created a table by displaying the current server memory usage, partition and available memory. For this, first of all retrieved the data from server by creating a java class and developed the required code. 2. Along with that created another page viz., Backup on fly tab.
| wipaydb tables doc |  |  | ½ hour |  |  | added some table informations in the wipaydb doc
2022-11-01 | WiPay Backup Tables interface | 1617 | 24 hours | 8 hrs |  | Need to display min timestamp of the source table using ajax. | 1.Created a java file, when we click on backup button in the interface then the control goes to this java page and based on the start date & end date [given manually in interface] the backup of the given table between these dates is done. And return to homepage. 2. After that developed a validation code for the destination table by using Ajax, when the destination table is not present in the database, error msg has to displayed on the screen , if its present then max timestamp of the destination table need to printed on the screen.
2022-12-01 | WiPay Backup Tables interface | 1617 | 24 hours | 8 hrs |  | Need to display the source table columns in the index column dropdown box dynamically. | 1. Extended the functionality by adding another method which is used to compress the csv files to gunzip(gzip) file format using SSH Connection. 2. Displayed the source table maximum timestamp and destination table minimum timestamp using ajax and onblur function in javascript. 3.Created another jsp file viz., WipayBackupReportindexColumns.jsp file to populate the columns of the source table in the indx column dropdown box dynamically. Still doing it.
18/01/22 | WiPay Backup Tables interface | 1617 | 24 hours | 8 hrs | add an external functionality [help], when we click on that it has to display the notes about the interface. | Adding fieldset tag to the html pages | 1. Added an extra jsp file that is used to populate the source and destination index columns dynamically when we click on the source or destination tables [Corresponding columns of the tables]. 2. Added another jsp file that is used to populate the total databases that are existing in the server. So we can display the database corresponding to the selected servers [WiPay, WiCMS, Dev]. 3. like wise when we select destination database then destination table list should be displayed dynamically. All these are done using ajax and json.
19/01/2022 | WiPay Backup Tables interface | 1617 | 24 hours | 8 hrs | Add an external functionality [help], when we click on that it has to display the notes about the interface. Write a document. | Working on “inserting the data from one table in one server to another table in another table” which is used to backup. | No |  |  | 1. Done the task by taking the backup of a table in two different databases. 2.For this created a separate class for connections of 3 servers. 3. So populated the tables based on the databases and servers. |  | No
20/01/2022 | WiPay Backup Tables interface | 1617 | 24 hours | 8 hrs |  | Need to be deployed in live. Working on it. | Yes |  |  | Added an external functionality ie., help icon which is used to provide notes for a particular interface. Here it is added for Table Backup Reports, WiPay Backup Table (Add) and WiPay Backup Table (Backup On The Fly). For this to be done, developed code for pop up window, when we click on that “info” icon on the interface, a pop window will be displayed on the same page without disturbing the existed interface. If we want to maximize and copy the notes, we can do it. |  | No
21/01/2022 | WiPay Backup Tables interface | 1617 | 24 hours | 1 hr |  |  | Yes |  |  | Done some grammatical changes in the notes which in help pop up window |  | No
| Android Studio |  |  | 5 hrs | Import the winews android project in android app and learn it. | Trying to understand the code and do some additional changes in the created application |  |  |  | Installed Android Studio app. Created a sample application and named it as MyFirstApplication. Written some code to get the IMEI number of a phone and built the application and ran it successfully. After that installed this myapp apk in my mobile and observed if it working or not. Got some exceptions, cleared them line by line. Again did the same process, finally got the required output. |  | NO
| Space problem |  |  | 2 hrs |  | Trying to increase the C drive space. |  | System got stuck as the available space in C drive is 200 MB. Takes lot of time while loading it. Got stuck with that for almost 1 and half hour. I think its going to crash if necessary actions are not taken. But I had no Idea about what to delete in that drive as it contains users information… |  | Tried to increase the space of c drive by deleting unnecessary files. |  | NO
22/01/2022 | Android Studio |  |  | 6 hrs | Need to start Paytm Report. | Got an exception 'Could not find method implementation() for arguments [directory 'libs'] on object of type org.gradle.api.internal.artifacts.dsl.dependencies.DefaultDependencyHandler.' and trying to resolve it. |  |  |  | Imported the Winews project in the android studio. Built the file and done some changes. Got some exceptions, solved them line by line. Still getting that exception.
24/01/2022 | Android Studio |  |  | 2 hrs |  | On hold |  |  |  | Tried to build the WiNews project in Android studio. Got sync exceptions, resolved them. Got exceptions while building, trying to resolve them.
| PayTm Transaction Report |  |  | 6 hrs |  | Developing Paytm Report in MVC Model. | No |  |  | 1. Analysed the interface and written a document of PaytmTransactionReport Analysis Document. After that, Created a PaytmTransactionReport.jsp class to make a view page. |  | No
25/01/2022 | WiPayAdmin Deployment. |  |  | 3 hrs | Deploy WiPay Backup Reports in live |  | Yes |  |  | Deployed the WiPayAdmin on live and observed the errors and exceptions. |  | Yes
| PayTm Transaction Report | #1624 | 24 hours | 5 hrs |  | Analysing the complete report once again as the new functionality is added. After that start the task in MVC | No |  |  | Done the complete analysis of the interface again because new functionality of refund status, tx status, refund are added. After that created servlet class, dao class, service class, Bean class and started writing code. |  | No
27/01/2022 | PayTm Transaction Report | #1624 | 24 hours | 7 hrs |  | Need to attach all these classes by requestDispatcher and populate the tables using ajax. | No |  |  | Created new bean, service, controller, dao and jsp classes in the project. And written all the required code for MVC architecture. |  | No
| Space problem |  |  | 1 hr |  |  | Yes |  |  | freed space in c drive. |  | Yes
28/01/2022 | PayTm Transaction Report | #1624 | 24 hrs | 8 hrs |  | Based on the trans status, we have to display transaction, refund status and inititate refund, we have to hit the urls to the operator. | No |  |  | Cleared all the exceptions. After that from paytm_transaction_report.jsp class using ajax, servlet [which is controller class] is called. Then this controller executes all the required methods based on the conditions passes to another jsp page which is paytm_transaction_report_db.jsp using requestDispatcher. Here the response got from controller is json response. Hence using this json response, the 4 tables are populated. |  | No
29/01/2022 | PayTm Transaction Report | #1624 | 24 hrs | 8 hrs | Deploy this report in live | Build Winews in Android Studio. | Yes |  |  | Based on the transaction status populated the remining tables by using json responses. Json response is obtained by firing the url for server to server connection in order to know the transaction status of the customer. |  | No
31/01/2022 | Android Studio |  |  | 4 hrs |  | Clear exceptions and Build the project | No |  |  | Tried to build the project Winews in android studio. Getting lots of exceptions and clearing them. |  | No
| Logs |  |  | 1 hr |  |  | Yes |  |  | Checked the access and server logs for a specified user .
| Deployement of WiPay and cbm | #1625 | 3 hrs | 3 hrs | Write a document for the changes made in those projects | checking the logs and billing for exceptions | Yes |  |  | Made the changes in VodaIdeaBillingProcessor.java & IdeaIBMBillingProcessor.java files in WiPay and IdeaIBMBillingProcessor.java & ViBillingProcessor.java files in cbm.jar by adding accouttype in the callback url and deployed both the projects in live. Observing the logs and billing. |  | No
2022-01-02 | Deployement of WiPay and cbm | #1625 | 3 hrs | 2 hrs |  |  | Yes |  |  | Written a document of the changes made in the WiPay and cbm and updated with redmine ticket |  | Yes
| Logs |  |  | 2 hrs |  |  | Yes |  |  | Retrieved the bill request and response logs of the idea and vodafone for each merchant to check whether the newly made changes are working or not and written a document and sent them to Abhishek |  | Yes
| PayTm Transaction Report | #1624 | 24 hrs | 4 hrs |  | draw a flow chart for the process. | No |  |  | Written redmine ticket document of paytm transaction report with several fields such as test cases, list of files changed etc., Also made changes in the analysis report. |  | No
2022-02-02 | PayTm Transaction Report | #1624 | 24 hrs | 8 hrs |  | Do the deployment once again by making style changes in the interface | No |  |  | 1. Prepared a final document for the paytm transaction report and attached to the redmine ticket. 2. Deployed in the live by making the changes with respective to live. |  | NO
2022-03-02 | PayTm Transaction Report | #1624 | 24 hrs | 3 hrs |  | Do the deployment once again by making style changes in the interface | No |  |  | Made changes by adding extra table and named it as Overall status in interface by taking the data from request_temp and paytm_history tables. |  | No
| Vi / curl request and response | #1627 |  | 5 hrs | [5 empty] | Changed the token url, username, password, service name. Service api and hit the curl command to generate accesstoken and replaced the curl command bearer with this access token and hit the url in the server.
2022-04-02 | PayTm Transaction Report | #1624 | 24 hours | 4 hrs |  |  | Yes |  |  | 1. Changes made in paytm_transaction_report_db.jsp by adding style tags in order to make the separation between History status tables[old view] and other status [New View]. 2. After that deployed the project in live and its working fine. Then committed it to svn. |  | Yes
| Wrapperprojects |  |  | 4 hrs |  | Currently knowing about the wrapper projects. |  |  |  | Took the svn checkout for the projects such as wrapper, wiPlayAndroid, PCW. After that imported the projects in eclipse and android studio. Observed the pcw document.
2022-05-02 | PayTm Transaction Report | #1624 | 24 hours | 2 hrs |  | Need to deploy in live. | Yes |  |  | Again done changes in the paytm_transaction_report_db by adding extra columns in some tables. |  | No
| Wrapperprojects |  |  | 2 hrs |  | Know about the projects | No |  |  | Observed the various documents in WrapperDocs
| WiPlayAndroid | #1630 | 16 hrs | 4 hrs |  | Build the project and install the apk | No |  |  | Imported the WiPlayAndroid project in Android studio and tried to build the file. Got some exceptions. Solved them. But still getting the exceptions and trying to solve them.
2022-07-02 | WiPlayAndroid | #1630 | 16 hrs | 8 hrs |  | Remove the google sign in button after sign in completed in the app. | No |  |  | 1. Solved the exceptions by changing gradle jvm path and deleting almost all files in .gradle folder in c drive. After that built the file and played in my android device. 2. Got exceptions, so again imported the project and built the project. Created a certificate of the keystore by using keytool in command promt. Got the sha1 fingerprint. This is added to google fire base. 3. After that ran the project in my android device again, finally its working fine. |  | No
2022-08-02 | Android Studio/ WiPlayAndroid/ WiNews | #1630 | 16 hrs | 8 hrs |  | Observe the PCW wrapper project | No |  |  | 1. Imported WiNews app in android studio and while building it, got some exceptions like .DefaultLenientConfiguration$ArtifactResolveException: Could not resolve all files for configuration ':app:debugCompileClasspath'. After solving them built the project and ran it a android device. But it couldn't load the news. 2. After that imported another winews app and ran the file and its working fine. |  | No
2022-09-02 | Android Studio/ WiPlayAndroid/ WiNews | #1630 | 16 hrs | 8 hrs |  | Set up the spring tool suite and work on it. | Yes |  |  | 1. Build is successful for android studio. 2. After that installed STS and done the setup. Created a sample project and ran that project in local host. |  | Yes
2022-10-02 | Power Cap/ WiPlayAndroid | #1635 | 16 hrs | 8 hrs |  | Wrapping | Yes |  |  | Updated my existing powecapActivity.java class. After that displayed User name after user signs in through google login page in WiPlay Android using TextView. |  | Yes
2022-11-02 | Power Cap/ WiPlayAndroid | #1635 | 16 hrs | 7 hrs |  | Display google account info such as User image, google mail id, User name etc. when Account info button is clicked as popup window. | No |  |  | 1.Learned about how to wrap the games in the powercap. 2. Created a popup button in WiPlayAndroid. By using this button, have to display user info. Getting exceptions, trying to solve them. |  | No
| Vi / curl request and response |  |  | 1 hr |  |  | Yes |  |  | Once again analyzed the Vi and prepared a excel sheet of the MT credentials in order to be changed in the code |  | Yes
14/02/22 | Power Cap/ WiPlayAndroid | #1635 | 48 hrs | 2 hrs |  | Display google account info such as User image, google mail id, User name etc. when Account info button is clicked as popup window. | No |  |  | done some changes in the code, but still getting exceptions. Trying to solve them. |  | No
| Vi MT Message Testing/cbm.jar | #1637 | 6 hrs | 6 hrs |  | Write design document | No |  |  | 1. Made some changes in the code and created an extra table for operator credentials. 2. Tested in the dev server. After testing committed the code and deployed in live servers and observed the billing. 3. Tested using curl command for both 55321 and 54767 if the messages are sending to the user. |  | No
15/02/2022 | Vi MT Message Testing/cbm.jar | #1637 | 6 hrs | 5 hrs |  | Write design document | No |  |  | Got a problem of storing multiple access tokens with same config id in voda_idea_access_tokens table after Migration. Observed the logs and rectified the problem by doing some changes in the ViBillingProcessor.java in cbm. After that deployed on live again and observed the logs and billing. Everything is perfect. |  | No
| WiPay Backup Tables | #1617 | 24 hrs | 3 hrs |  | Deploy on live | No |  |  | Once again tested the interface by taking the backup in a csv file as well as in a separate table in the same db. Working fine. |  | No
16/02/2022 | WiPay Backup Tables | #1617 | 24 hrs | 5 hrs | [5 empty] | Set every thing right for today backup. Inserted extra table in sms_history in wipay_backup_tables in wipaydb which takes the backup into csv file. Here csv location is in 19 server.
| Spring boot sample Project | #1641 |  | 3 hrs | [5 empty] | Installed new spring tool suite in local system and made a setup. Created a sample project and tried to insert data into the database using service and main class
17/02/2022 | WiPay Backup reports |  |  | 1 hr | [5 empty] | Observed the logs and the memory.
| Exam |  |  | 3 hrs | [5 empty] | attended an exam
| Spring boot project | #1641 |  | 4 hrs |  | Implementing image object in the spring boot |  |  |  | Tried to impement the image object. Made connections with data base. Getting errors when tried to get the data.
18/02/2022 | Spring boot project | #1641 |  | 6 hrs |  | Store the values in the database using rester. |  |  |  | 1. Written an impact analysis document. 2. After that created objects for content and image and got the response based on id. After that converted into json format successfully. Trying to hit the url using poster to store the values directly into the database. Getting errors. Trying to resolve them
| wiapp | #1644 | 6 hrs | 2 hrs |  | Dump the tables into live |  |  |  | 1. Analysed the wiapp database in the dev to dump that into live database.
19/02/2022 | Spring boot project | #1641 |  | 1 hr |  | Store the values in the database using rester. |  |  |  | Tried to hit the url in poster. But getting error. Trying to solve it.
| wiapp | #1644 | 5 hrs | 4 hrs |  |  | Yes |  |  | 1. Dumped the tables from dev server to live server. And stored them in home/brahmini/wiapp.sql. 2. Next copied the wiapp data from /data/wiapp in dev server to both 13 and 152 server /data/wiapp using linux commands. 3. After that committed the wiappAdmin jsp classes. |  | No
| self Evaluation of exam |  |  | 1 hr |  |  | Yes |  |  | Evaluated the exam report and made a document. |  | Yes
| Vi MT Message Testing/cbm.jar | #1637 | 6 hrs | 2 hrs |  |  | Yes |  |  | Prepared the design document. |  | Yes
21/02/2022 | wiapp | #1644 | 10 hrs | 8 hrs |  | write document about the manage customer service settings. | No |  |  | 1. Learned how to fill the details in the manage service interface, manage customer interface and edited the setting in the required format in wiapp. Based on these settings we get the user interface of the wiapp. 2. Writing the document about these settings, what needs to be provided to get the proper wiapp interface |  | No
22/02/2022 | wiapp | #1644 | 10 hrs | 2 hrs |  |  | Yes |  |  | Completed the page setting document about the customer setting. |  | No
|  | #1647 | 10 hrs | 6 hrs |  | Test in dev dynamically. | No |  |  | 1. Here task is to “Use form post instead of query string parameters in wiapp redirections” which we are getting large url when we click on a specific category of games in wiapp menu. So instead of that we need only https://dev.wicore.in/wiapp/index. 2. So, first in the code I have added form tag and changed the code. 3. After that written a static html page with java script by passing the dev url and post method to the form tag and tested it. It is successfully executed. Now try this code dynamically. |  | No
23/02/2022 | wiapp | #1647 | 15 hrs | 8 hrs |  | Render the news content by clearing exceptions. | No |  |  | Added form tags in the htmlUtility.java class and stored the java script in /data/wiapp/WiappElements/content/CardVerticalContent/js/wi_games.js location. So by hitting the wiapp page using post method no links are displayed. After that did the same thing for viewall icon. Got some exceptions and cleard it. After that edited the view more button to provide more games. Got some exceptions. Need to clear them. |  | No
24/02/2022 | wiapp | #1647 | 15 hrs | 5 hrs |  | Enable Google sign in button | No |  |  | 1. Cleared the exceptions and got the news. 2. Need to enable google sign in. |  | No
| wiapp | #1649 | 2 hrs | 3 hrs |  |  | Yes |  |  | Done the changes in the html and style.css files for the billing user page. |  | No
| Test Paper document |  |  | 2 hrs |  | Write the answers for the remaining questions. | No |  |  | Written a answers document for some questions. Need to answer remaining questions. |  | No
25/02/2022 | wiapp | #1647 | 15 hrs | 7 hrs |  | work on login page | No |  |  | Enabled the google sign in button. After that done the logo changes and merged the code . |  | No
| Test Paper document |  |  | 1 hr |  |  | Yes |  |  | Done the exam paper document. |  | Yes
26/02/2022 | wiapp | #1647 | 15 hrs | 3 hrs | [5 empty] | Here adjusted the google sign in button in the wiapp interface. And observed the wiapp flow. |  | No
2022-01-03 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  |  | No |  |  | 1. inserted the extra rows in customer_service_page_settings_value, wi_service_pages, cust_ser_pg_conf for default settings. 2. After that edited the some changes in wiapp. 3. Then we need to create a default settings for new service customer as well as old one. After that when we click on settings there will be default settings in the settings page with predefined values. So done the changes in the CustomerServicePageSettingsAddEdit.jsp, customer_service_page_settings.jsp, CustomerServicePageIDs.jsp |  | No
2022-02-03 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  |  | No |  |  | 1. checked out the code into svn for default settings. 2. deleted the Asset Location & Logo Location text boxes in manage customer settings, added wiapp_url in that place and stored the values in db. And added file upload browse button in customer page settings and stored the files in a particular location in dev. 3. Edited html utility to make correct alignment. 4. Suppressed the arrayIndexOutOfBoundsException and get the news page with out any error. |  | No
2022-03-03 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  |  | No |  |  | 1. Modified the changes in the file upload button. After that stored the location path in customer_service_page_settings_value table. Done the required changes and commited to svn. 2. Documented the script changes that needs to done in live. |  | No
2022-04-03 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  |  | No |  |  | Done all the changes like transferring the data from the tables. Fixed issues for logo upload and content. Transeferred the content like logos, assets etc., from dev to live servers |  | No
2022-05-03 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  | Replace the hard coded values with the live settings. | No |  |  | Done the changes like copied the required folders [edited] data from local to live servers. And noted down all the hardcoded urls in the dev server and trying to change them in live. After that observed the live server and compared it with the dev server by checking any of the pages are displaying or not. And noted any one of the changes required. |  | No
2022-07-03 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  | Check all the settings are working or not in WiAppAdmin | No |  |  | 1. Removed the wiapp_url and home_url in the manage customer settings. 2. Inserted an extra setting wiapp_url in settings table in wiapp database. After that created SettingsDAO class to get the required url from the table by sending constant WIAPP_URL as s_filed to the method. After that replaced all the static urls with the wiapp_url in almost 7 classes. 3. Removed the top style css in desktop_menu.css in TopLeftMenu.css in menu category to make the categories constant and work properly and adjusted the css according to the requirements . |  | No
2022-08-03 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  | Testing the billing process. | No |  |  | 1. Removed the home & wiapp url textboxes completely. Done the required changes in Billing Interfaces for proper table structure. Adjusted the Back button by using window.close() method in js to work the back button correctly. After that commited all these changes to svn. 2. Observed the billing process code flow in wiapp. |  | No
2022-09-03 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  | Test the billing process | No |  |  | 1. Replaced the settingsURL with settingValue() in wiapp and committed in svn. 2. Also added settingdao class in WiappAdmin to get the url dynamically and committed in svn. 3. Observed the bill flow and tested some cases in billing. |  | No
2022-10-03 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  | Testing the billing process | No |  |  | Done the billing to observe the two test cases. Billing is working properly. But when the cookies are deleted its not working properly. Because of that changed the code in index.java and CookieUtility.java and testing the billing again |  | No
2022-11-03 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  | Testing the billing process. Google sign in user is not storing in the request and wi_action table. Need to store those values. Change the logic to avoid creating new cookieid and user_id when there is already cookie_id and user_id. | No |  |  | 1. Tested all the msisdn cases and according to the testing modified the code in the wiapp project. Along with that added extra columns [customer id, service id, telco id] in wi_msisdn_info table in wiapp database to store the corresponding values in the columns. So for that values to store, done some changes in the code. 2. Testing some cases with google sign in. Done some changes in the code.
14/03/22 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  | Billing for google sign in need to be tested | No |  |  | 1. Started testing for google sign. Here after billing when the user signs out and signs in again, we are not getting the content. For this created an extra method to get the previously existed cookie from both wi_user_info and cookie_info tables. And modified the code to store the gmail in request and process_request table. 2. Prepared an excel document for customer_page_settings and their descriptions for each setting. |  | No
15/03/2022 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  | Billing for google sign in need to be tested. Getting issues trying to solve them | No |  |  | 1. Written java script code to display alert when the user doesn't sign in or turned on mobile data. Passed the required parameters in HtmlUtility.java. In content utility created a json object to store the user details and returned to index. 2. Written impact analysis document for this 3. Testing the google signin billing using cookies. |  | No
16/03/2022 | wiapp and WiAppAdmin | #1659 |  | 8 hrs |  | Testing almost completed. One test case is left. Need to fix the issue. Write the document. | No |  |  | 1. Created an extra method manageCookies() in the CookieUtility.java. Freshly implemented the conditions. And removed the unnecessary code from the index.java and placed all these code in this method. 2. After that started testing all the test cases with msisdn and google signin. All are working almost fine. Need to fix some issues. |  | No
17/03/2022 | wiapp and WiAppAdmin | #1659 |  | 4 hrs |  | Some issues are there need to be fixed. | No |  |  | 1. Created a form post method in HtmlUtility.java and called from the renderHtml.java. 2. Later committed all the required changes to SVN. |  | NO
| WiPayAdmin/ User History Events Interface. | #1654 | 24 hours | 4 hrs |  | Fetching the details from the CSV files in the background. | No |  |  | 1. Prepared analysis document for the User History Events Interface. 2. After that created menu details in the database. 3. Created User Interface. But need to be do the background process. |  | NO
18/03/2022 | WiPayAdmin/ User History Events Interface. | #1654 | 24 hours | 8 hrs |  | Fetch the records based on time stamp. | No |  |  | Done the interface by getting the sample files from the csv based on msisdn, order id and transid. And displayed in the table format. |  | No
19/03/2022 | WiPayAdmin/ User History Events Interface. | #1654 | 24 hours | 8 hrs |  | last data is printing . Need to fix this issue | No |  |  | Fetched the data from the csv files based on timestamp, msisdn, order_id, transid. Going to print the data in the format using json. But the last data is recurring. Need to fix the issue. |  | No
21/03/2022 | WiPayAdmin/ User History Events Interface. | #1654 | 24 hours | 7 : 15 hrs |  | Almost done. Implement extra feature ToDate. Write the Final document. | Yes |  |  | Done the interface completely. Now we can get the user records based on msisdn or orderID or TransID and Date. Here merchant and network are in the form of id's, inorder to convert them in to name we used servletcontext concept and Hashtable. Using this we converted them to group names. Implemented new method to get the csv location. |  | No
| Scrum call |  |  | 45 minutes
22/03/2022 | WiPayAdmin/ User History Events Interface. |  | 24 hours | 6 hrs |  | Code Review. Write Final Document. | Yes |  |  | Got an issue while displaying the data using split method. Done some changes in the code. And finally its working. |  | No
| Deployement of SMSHistoryHourlyWiseAggregation |  |  | 2 hrs |  |  | Yes |  |  | Deployed the SMSHistoryHourlyWiseAggregation project in live[152 server], and observed whether the data is storing properly or not. |  | Yes
23/03/2022 | WiPayAdmin/ User History Events Interface. | #1654 | 24 hours | 5 hrs |  | Code Review | Yes |  |  | 1. Got an issue, which is the data is located in 19 server and we will deploy the interface in 152 server, so in order to establish the connection created reportuser.cfg file in /usr/appserver/wipay [in 152 server] with host, username, password of 19 server. 2. Completed the final design document and uploaded in redmine. |  | No
| Wiapp/ Billing page | #1649 |  | 1 hr |  |  | Yes |  |  | Completed the final design document. And uploaded in to redmine.
| Live Deployment |  |  | 1 hr |  |  | Yes |  |  | Deployed WiPayAdmin in live of sms history aggregation hourly |  | Yes
| Scrum call |  |  | 1 hr |  | Complete all the wiapp design doc | Yes |  |  | Scrum call and redmine tickets updation. |  | Yes
24/03/2022 | WiPay Backup reports | #1657 |  | 5 hrs |  | Fix the issue [CORS] | No |  |  | Done the live deployment. Got some issues in live but when running in dev its working fine. |  | No
| SMS History Aggregation |  |  | 3 hrs |  | Need to deploy in live again | No |  |  | data is not storing correctly, need to deploy it again |  | No
25/03/2022 | WiPay Backup reports | #1657 |  | 3 hrs |  | Need to deploy in live again. | No |  |  | Observed the code once again and done some changes in the code in order to populate the index columns dynamically. Now its working fine. Need to deploy in live. |  | No
| WiApp/ WiAppAdmin Demo |  |  | 1 ½ hrs | [5 empty] | Attended the demo of wiapp .
| Production/Billing issue |  |  | 3 and half hours | [5 empty] | Billing is stopped for vodafone. Checking the issue.
26/03/2021 | WiApp/ WiAppAdmin | #1659 |  | 5 and half hours |  | Check the billing flow in wiapp | No |  |  | Checked the billing, done some changes in wiapp like removing signout button, when the user signins in . After that rearranged the alert to display the alert message when user clicks on content with out signin or enable mobile data. |  | No
28/03/2022 | WiApp/ WiAppAdmin | #1659 |  | 8 hours |  | Do some changes in the google_signin.js file to validate the user [google login bill flow] | No |  |  | Checked the all the MSISDN test cases. All are working perfectly. But for, google sign in only two test cases are working. Need to do some changes to proceed. |  | No
29/03/2022 | WiApp/ WiAppAdmin | #1659 |  | 8 hours |  | Almost done. Need to do final bill testing. Write final document. | No |  |  | 1. Edited the google_signin.js by adding ajax call, but it is not worked. 2. After that, created a form tag in javascript and sent the tokenID to the index page usign hidden input tag. Based on the tokenID , got the email and other variables. 3. Finally done the testing. Working properly. Need to do final testing. |  | No
30/03/2022 | WiApp/ WiAppAdmin | #1659 |  | 8 hours |  | Write the document. | No |  |  | 1. Done all the test cases. Made some changes in the code. All the test cases are working properly. 2. There are two test cases, yet to be done. Present they are on hold. 3. Edited the Impact analysis document. Started writing final document. |  | No
31/03/2022 | WiApp/ WiAppAdmin | #1659 |  | 8 hours |  | Make the required changes | No |  |  | 1. Written the document 2. Added a method HTMLUtility.addTabbaleSpecialContent(parentEle,reqJSONArr,doc); to provide some header tags. |  | No
2022-01-04 | WiApp/WiAppAdmin | #1659 |  | 4 hours |  |  | Yes |  |  | 1. Done the final documentation 2. Done some changes in the wiapp and committed in live. |  | Yes
| WiAds |  |  | 1 hour |  | understand the flow of wiAds and up the porject | No |  |  | Enabled the banners in wi games and understanding the flow of WiAds Project. |  | No
| WiPayAdmin local setup |  |  | 3 hours |  | Getting password issue. Need to fix it. | No |  |  | Made the mysql and jboss run locally. Deployed the project. Getting login issue. |  | No
2022-04-04 | WiApp/WiAppAdmin deployment |  |  | 4 hours |  |  | Yes |  |  | Deployed the SMSHistoryHourlyWiseAggregation project in live[152 server], and observed whether the data is storing properly or not. 2. Deployed the WiAppAdmin project in live, observed the logs. |  | Yes
| WiAds |  |  | 2 hrs |  | Study about WiAds and understand it. | No |  |  | 1. Observed the WiAds, Written a small document about the code flow. 2. Modified the data in the wi_banners table, to display the banners correctly in wiapp portal. |  | No
| Logs |  |  | 1hr |  |  | Yes |  |  | Fetched the logs from cbm.jar and WiPay for Vi |  | Yes
2022-05-04 | WiAds/WiApp |  |  | 4 hours |  | Make the required changes | No |  |  | 1. Understood the flow of the wiAds project b observing the database and code. 2. Made some changes in HtmlUtility.java, to remove the unwanted dots that are appearing on banners. 3. Displayed the banners for androidApps, by editing the column wi_services table[provided url for wi_ads_api]. |  | No
| Logs |  |  | 1 hour |  |  | Yes |  |  | 1. Observed the billing and the logs if there are any exceptions.
| WiPayAdmin |  |  | 3 hours |  | after verification, need to add some actions in action_codes table in live | No |  |  | For Vi, Bill requests are not displaying in WiPay Action Summary Report Hourly report, Analysed the code, made the required changes in the database. They are displaying in dev. Need to make the changes in live. |  | No